## Summary Dashboard
SVaaN GLOBAL TECH — DIGITAL ASSET & ICON REQUIREMENTS
Master Technical Audit, Responsive Dimension Specifications, and Production Delivery Roadmap
PROJECT ASSET HEALTH METRICS
TOTAL ASSETS AUDITED | AVAILABLE & ACTIVE | NEEDS REPLACEMENT | MISSING ASSETS | HIGH PRIORITY TASKS | READY PERCENTAGE
69 | 55 | 8 | 6 | 46 | 80%
ASSET BREAKDOWN BY CATEGORY |  |  | ASSET BREAKDOWN BY PRIORITY
Category Sheet | Total Items | Status Health | Priority Level | Count | Action Turnaround
Images & Illustrations | 22 | 14 OK / 8 Action | High Priority | 46 | Immediate Sprint (Day 1 - 3)
Icons & SVGs | 33 | 33 OK / 0 Action | Medium Priority | 22 | Standard Sprint (Week 1)
Logos & Brand Assets | 8 | 2 OK / 6 Action | Low Priority / Polish | 1 | Pre-launch Refinement
Animations & Micro-Interactions | 6 | 6 OK / 0 Action | All Tracked Items | 69 | Full Verification Matrix
CRITICAL DESIGN & DEVELOPMENT ACTION ITEMS
Action #1: Replace Stock Unsplash Placeholders | Unsplash images are actively used in AboutSection (team collaborating), about/page.tsx (origin story), and BlogSection (3 insight posts). Replace with authentic SVaaN office photography and branded 3D editorial illustrations.
Action #2: Design Bespoke OpenGraph Social Card (1200x630) | Social sharing currently relies on the square 1254x1254 hero visual. Provide a 1200x630 1.91:1 high-impact OpenGraph card with the SVaaN primary logo, tagline, and blue brand gradient for LinkedIn/Twitter previews.
Action #3: Supply Reverse White Vector Logo for Dark Footers | FooterV2 currently forces a white card container around Primary_logo.svg. Creating svaan-logo-white.svg will allow direct placement onto the dark mesh footer background with modern transparent styling.
Action #4: Provide Production App Mockups for Case Studies | Replace pure code-based SVG illustrations for Biblical Touring, Fareeda Homecare, Siloam, MMU, and Havendeeds with high-fidelity tablet/mobile UI screen mockups inside modern device frames.
Action #5: Mobile PWA & Apple Touch Icons Generation | Export apple-touch-icon.png (180x180), icon-192.png, and icon-512.png to ensure crisp rendering on iOS/Android home screens and satisfy 100/100 PWA Lighthouse audits.
PRODUCTION FILE SPECIFICATIONS & ENCODING RULES
Next.js Image Loader | All raster graphics must be WebP/AVIF with Next.js <Image /> component, explicit width/height or fill, and priority on above-the-fold assets.
Vector SVGs Standard | Must be sanitized, viewBox defined, width/height omitted or class-driven, and SVGO minified to remove unnecessary XML tags.
Raster Compression | Max raster file size targets: Hero < 200 KB, Section cards < 80 KB, Thumbnails < 40 KB, Icons < 10 KB. Quality target 80-85% lossy.
Aspect Ratio Consistency | Portraits: 4:5 (400x500px); Editorial Blog Cards: 5:3 (800x480px); Case Studies: 3:2 (1200x800px); Social OG: 1.91:1 (1200x630px).

## Images & Illustrations
Page | Section | Image / Icon Title | Asset Type | File Format | Required Width (px) | Required Height (px) | Aspect Ratio | Description / Purpose | Desktop / Tablet / Mobile Requirement | Priority | Current Asset Status | Recommended File Name | Notes
Home (/) | HeroSection | Isometric Tech Sphere & Circuit Graphic | Image | WebP / AVIF | 1254 | 1254 | 1:1 | Main 3D hero visualization showcasing interconnected digital engineering, AI nodes, and enterprise infrastructure. | Desktop: 627x627 display (2x retina); Mobile: 360x360 scaled center | High | Available | herosection.webp | Active in /public. Verified 198 KB WebP. Already optimized with priority flag in Next.js.
Home (/) | AboutSection | SVaaN Engineering Team Collaboration | Image | WebP / AVIF | 800 | 600 | 4:3 | Team photograph representing engineering collaboration, sprint planning, or modern office culture. | Desktop: 50% split container; Tablet/Mobile: Full width stacked | High | Needs Replacement | svaan-team-collaboration.webp | Currently using Unsplash placeholder (photo-1522071820081-009f0129c71c). Needs authentic SVaaN office/team photography.
Home (/) | BlogSection (Post 1) | Business Context Before Code - Editorial Card | Image | WebP / AVIF | 800 | 480 | 5:3 (1.67:1) | Editorial article banner for strategic technology decision-making and product discovery. | Desktop: 3-col grid card (380px w); Mobile: 1-col full width card | Medium | Needs Replacement | insight-business-context.webp | Currently Unsplash photo-1552664730-d307ca884978. Replace with custom branded 3D/editorial abstract graphic.
Home (/) | BlogSection (Post 2) | Small Tech Decisions - Editorial Card | Image | WebP / AVIF | 800 | 480 | 5:3 (1.67:1) | Editorial article banner illustrating system architecture consistency and software quality. | Desktop: 3-col grid card; Mobile: 1-col full width card | Medium | Needs Replacement | insight-tech-decisions.webp | Currently Unsplash photo-1517694712202-14dd9538aa97. Needs bespoke SVaaN branded graphic.
Home (/) | BlogSection (Post 3) | AI Legacy Modernization - Editorial Card | Image | WebP / AVIF | 800 | 480 | 5:3 (1.67:1) | Editorial article banner for AI automation intersecting with existing enterprise architectures. | Desktop: 3-col grid card; Mobile: 1-col full width card | Medium | Needs Replacement | insight-ai-modernization.webp | Currently Unsplash photo-1620912189865-1e8a33da4c5e. Needs bespoke SVaaN branded graphic.
Global (All Pages) | Footer / FooterV2 | Geometric Circuit & Cloud Grid Mesh Texture | Image | WebP | 1920 | 800 | 24:10 (2.4:1) | Subtle dark tech textured background image applied behind footer navigation and corporate copyright. | Desktop: Full width stretch; Mobile: Center crop with CSS overlay | High | Available | footer-bg.webp | Active in /public. Optimized to 34.7 KB WebP. Works seamlessly with dark gradient overlay.
About (/about) | StorySection | SVaaN Founding Journey & Origin Story | Image | WebP / AVIF | 1200 | 800 | 3:2 | Visual showcase for SVaaN origin in 2021, starting with single application-support engagement in the US. | Desktop: 520px container height; Mobile: 360px container height | High | Needs Replacement | svaan-origin-story.webp | Currently uses Unsplash stock (photo-1552664730-d307ca884978). Needs genuine founder/early company picture or brand visual.
About (/about) | GlobalDeliverySection | Interactive World Map Vector Graphic | Illustration | SVG | 4378 | 2060 | 2.12:1 | Hi-res world map with coordinates for Chennai HQ, US, UK, Canada, and UAE delivery hubs. | Desktop: Aspect-ratio 2.12:1 container with interactive pins; Mobile: Scrollable map with bottom pin cards | High | Available | svaan-map.svg | Active in /public (380 KB). Successfully powers responsive geolocation pins and delivery pod modals.
About (/about) | DeliveryHubs | Chennai HQ Operations & Floor Photo | Image | WebP / AVIF | 800 | 600 | 4:3 | Chennai headquarters facility, 60+ engineer dev center, and round-the-clock operations pod. | Desktop: Modal / Hub detail view; Mobile: Hub accordion image | Medium | Missing | chennai-hq-operations.webp | Recommended to enrich interactive map modal with genuine Chennai development centre photo.
Leadership (/leadership) | Leadership Grid | Dinesh Natarajan - Executive Portrait | Image | WebP / AVIF | 400 | 500 | 4:5 | Professional executive portrait of Dinesh Natarajan, Founder of SVaaN Global Tech. | Desktop: 400x500 card; Mobile: Scaled 300x375 with sticky bio | High | Available | dinesh.webp | Active in /public (73.1 KB). Verified high quality portrait with transparent/dark background.
Leadership (/leadership) | Leadership Grid | Sai Ramamurthy - Executive Portrait | Image | WebP / AVIF | 400 | 500 | 4:5 | Professional executive portrait of Sai Ramamurthy, CEO of SVaaN Global Tech. | Desktop: 400x500 card; Mobile: Scaled 300x375 with sticky bio | High | Available | Sai.webp | Active in /public (70.4 KB). Verified high quality portrait with clean corporate framing.
Work (/work) | WorkShowcase (Case 1) | Biblical Touring - Dual Platform App Visual | Illustration | SVG / WebP | 1200 | 800 | 3:2 | Showcase visual representing the travel operations web portal and offline-first tourist mobile guide app. | Desktop: Bento case card & Detail hero; Mobile: Scaled card banner | High | Available | case-biblical-touring.svg | Currently rendered via custom SVG Isometric illustration (Illustrations.Touring). Hi-res app mockup recommended for case page.
Work (/work) | WorkShowcase (Case 2) | Fareeda Homecare - EVV Mobile & Dispatch Visual | Illustration | SVG / WebP | 1200 | 800 | 3:2 | Showcase visual for healthcare agency dispatch portal, EVV compliance, and family care feed app. | Desktop: Bento case card & Detail hero; Mobile: Scaled card banner | High | Available | case-fareeda-homecare.svg | Currently rendered via Illustrations.HomeCare component. Dedicated UI screen mockups recommended for deep-dive case page.
Work (/work) | WorkShowcase (Case 3) | Siloam - Telemedicine & EHR Suite Visual | Illustration | SVG / WebP | 1200 | 800 | 3:2 | Visual for clinician WebRTC portal, digital prescriptions, and patient appointment booking mobile app. | Desktop: Bento case card; Mobile: Scaled card banner | High | Available | case-siloam-healthcare.svg | Currently rendered via Illustrations.Healthcare component. Production tablet/mobile mockup recommended.
Work (/work) | WorkShowcase (Case 4) | MMU - Multi-Property Asset Management Visual | Illustration | SVG / WebP | 1200 | 800 | 3:2 | Showcase visual for real estate portfolio analytics, automated rent collections, and tenant dispatch portal. | Desktop: Bento case card; Mobile: Scaled card banner | High | Available | case-mmu-assetmanagement.svg | Currently shares Illustrations.PropTech component. Dedicated multi-asset dashboard illustration recommended.
Work (/work) | WorkShowcase (Case 5) | Havendeeds - PropTech Title & Escrow Platform Visual | Illustration | SVG / WebP | 1200 | 800 | 3:2 | Showcase visual for digital closing platform, verified title deed registry, and spatial property search. | Desktop: Bento case card; Mobile: Scaled card banner | High | Available | case-havendeeds-proptech.svg | Currently rendered via Illustrations.PropTech component. Product screenshot mockup recommended.
Solutions (/solutions/build) | SolutionHero | Build Solution - Custom Digital Platform Banner | Illustration | SVG / WebP | 800 | 800 | 1:1 | 3D isometric engineering illustration representing new digital product builds, MVPs, and web/mobile apps. | Desktop: Right split hero block; Mobile: Centered below title | Medium | Available | solution-build-hero.svg | Currently powered by Icons3D.Build isometric vector with floating nodes.
Solutions (/solutions/modernize) | SolutionHero | Modernize Solution - Architecture Evolution Banner | Illustration | SVG / WebP | 800 | 800 | 1:1 | Isometric visualization showing legacy monolith transformation into modular microservices & cloud native systems. | Desktop: Right split hero block; Mobile: Centered below title | Medium | Available | solution-modernize-hero.svg | Currently powered by Icons3D.Modernize isometric vector with floating layers.
Solutions (/solutions/operate) | SolutionHero | Operate Solution - 24/7 Live Monitoring Banner | Illustration | SVG / WebP | 800 | 800 | 1:1 | Visual showing system reliability, continuous observability, SLA response desk, and DevOps maintenance. | Desktop: Right split hero block; Mobile: Centered below title | Medium | Available | solution-operate-hero.svg | Currently powered by Icons3D.Operate isometric support desk vector.
Solutions (/solutions/evolve) | SolutionHero | Evolve Solution - Continuous Growth & AI Banner | Illustration | SVG / WebP | 800 | 800 | 1:1 | Visual illustrating iterative roadmap planning, automation flywheels, and scaling product performance. | Desktop: Right split hero block; Mobile: Centered below title | Medium | Available | solution-evolve-hero.svg | Currently powered by Icons3D.Evolve flywheel vector.
Careers (/careers) | Culture & Benefits | SVaaN Engineering Life & Culture Graphic | Image | WebP / AVIF | 1200 | 675 | 16:9 | Photo grid or banner portraying developer workstation culture, hackathons, and learning pods. | Desktop: 1200px container; Mobile: 100% viewport width | Medium | Missing | svaan-careers-culture.webp | Will boost recruitment conversions and convey high-performance company atmosphere.
Contact (/contact) | ContactHero | Consultation & Inquiry Isometric Graphic | Illustration | SVG / WebP | 600 | 600 | 1:1 | Decorative communication visual indicating active consultation, response within 24 hours, and NDAs. | Desktop: Sidebar visual next to form; Mobile: Hidden or scaled top pill | Low | Missing | contact-consultation-graphic.svg | Enhances trust on enterprise lead capture form next to direct email/phone cards.

## Icons & SVGs
Page | Section | Image / Icon Title | Asset Type | File Format | Required Width (px) | Required Height (px) | Aspect Ratio | Description / Purpose | Desktop / Tablet / Mobile Requirement | Priority | Current Asset Status | Recommended File Name | Notes
Shared / Multiple | Icons3D Component | Cloud Infrastructure 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric layered floating cloud computing platform with animated pulsing gradients. | Vector SVG viewBox 0 0 100 100; Scales to 40x40 (cards) or 80x80 (heroes) | High | Available | Icons3D.Cloud (embedded SVG) | Used in ServicesGrid, CapabilitiesGrid, and TechStack. Built with CSS keyframe float animations.
Shared / Multiple | Icons3D Component | Database & Data Pipeline 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric multi-tier database cylinders with data flow connecting lines. | Vector SVG viewBox 0 0 100 100; Responsive display | High | Available | Icons3D.Database (embedded SVG) | Used in ServicesGrid, CapabilitiesAccordion, and TechStack Data section.
Shared / Multiple | Icons3D Component | Software Product Engineering 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric modular code block matrix symbolizing enterprise software engineering. | Vector SVG viewBox 0 0 100 100; Responsive display | High | Available | Icons3D.Software (embedded SVG) | Used in CapabilitiesGrid and Solution Bento components.
Shared / Multiple | Icons3D Component | UI/UX & Product Design 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric design canvas with layering planes, wireframe grid, and layout cursor. | Vector SVG viewBox 0 0 100 100; Responsive display | High | Available | Icons3D.Design (embedded SVG) | Used in Product & Experience capability section.
Shared / Multiple | Icons3D Component | Strategy & Advisory 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric strategic compass / target with directional vectors and milestone node. | Vector SVG viewBox 0 0 100 100; Responsive display | High | Available | Icons3D.Strategy (embedded SVG) | Used in Strategy & Advisory capability cards.
Shared / Multiple | Icons3D Component | Managed Support & Reliability 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric shield and uptime gear symbolizing continuous SLA maintenance. | Vector SVG viewBox 0 0 100 100; Responsive display | High | Available | Icons3D.Support (embedded SVG) | Used in Operate solution pillar and Support capabilities.
Shared / Multiple | Icons3D Component | AI & Automation 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric neural network diamond with illuminated synaptic connections. | Vector SVG viewBox 0 0 100 100; Responsive display | High | Available | Icons3D.AI (embedded SVG) | Used in AI automation solutions and TechStack.
Shared / Multiple | Icons3D Component | Mobile Engineering 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric mobile device slate showing app interface elements and floating gesture ripple. | Vector SVG viewBox 0 0 100 100; Responsive display | High | Available | Icons3D.Mobile (embedded SVG) | Used in Frontend & Mobile domain in TechStack.
Shared / Multiple | Icons3D Component | Backend Systems 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric clustered server towers connected by high-speed bus lines. | Vector SVG viewBox 0 0 100 100; Responsive display | High | Available | Icons3D.Backend (embedded SVG) | Used in Backend domain in TechStack.
Shared / Multiple | Icons3D Component | Microservices & API 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric decoupled container blocks communicating over gRPC/REST protocols. | Vector SVG viewBox 0 0 100 100; Responsive display | High | Available | Icons3D.Microservices (embedded SVG) | Used in Architecture and Modernization sections.
Approach (/approach) | ProcessSection | Process Phase 1: Discover 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric magnifying diagnostic lens on system schematics. | Vector SVG viewBox 0 0 100 100 | Medium | Available | Icons3D.ProcessDiscover (embedded SVG) | Step 1 in engineering delivery methodology.
Approach (/approach) | ProcessSection | Process Phase 2: Shape 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric architecture blueprint grid with modular system foundations. | Vector SVG viewBox 0 0 100 100 | Medium | Available | Icons3D.ProcessShape (embedded SVG) | Step 2 in engineering delivery methodology.
Approach (/approach) | ProcessSection | Process Phase 3: Prototype 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric interactive test harness with rapid validation nodes. | Vector SVG viewBox 0 0 100 100 | Medium | Available | Icons3D.ProcessPrototype (embedded SVG) | Step 3 in engineering delivery methodology.
Approach (/approach) | ProcessSection | Process Phase 4: Build & Scale 3D Icon | Icon | SVG | 100 | 100 | 1:1 | Isometric automated assembly and deployment pipeline. | Vector SVG viewBox 0 0 100 100 | Medium | Available | Icons3D.ProcessBuild (embedded SVG) | Step 4 in engineering delivery methodology.
Home (/) & Solutions | TechStack (Frontend) | Next.js Official Vector Logo | Icon | SVG | 48 | 48 | 1:1 | Official Next.js N vector emblem. | Scales inside 48x48 badge circle across all screen sizes | High | Available | tech-nextjs.svg | Rendered in TechStack frontend group.
Home (/) & Solutions | TechStack (Frontend) | React & React Native Atom Vector | Icon | SVG | 48 | 48 | 1:1 | Cyan React orbital atom vector logo. | Scales inside 48x48 badge circle | High | Available | tech-react.svg | Rendered in TechStack frontend group.
Home (/) & Solutions | TechStack (Frontend) | TypeScript Blue Shield Vector | Icon | SVG | 48 | 48 | 1:1 | Official TS square vector logo. | Scales inside 48x48 badge circle | High | Available | tech-typescript.svg | Rendered in TechStack frontend group.
Home (/) & Solutions | TechStack (Backend) | Node.js Hexagonal Vector Logo | Icon | SVG | 48 | 48 | 1:1 | Node.js green hexagon vector logo. | Scales inside 48x48 badge circle | High | Available | tech-nodejs.svg | Rendered in TechStack backend group.
Home (/) & Solutions | TechStack (Backend) | Python Dual Serpent Vector Logo | Icon | SVG | 48 | 48 | 1:1 | Python blue and yellow serpent logo. | Scales inside 48x48 badge circle | High | Available | tech-python.svg | Rendered in TechStack backend group.
Home (/) & Solutions | TechStack (Backend) | Go (Golang) Vector Logo | Icon | SVG | 48 | 48 | 1:1 | Go cyan speed typography logo. | Scales inside 48x48 badge circle | Medium | Available | tech-golang.svg | Rendered in TechStack backend group.
Home (/) & Solutions | TechStack (Cloud) | Amazon Web Services (AWS) Vector Logo | Icon | SVG | 48 | 48 | 1:1 | AWS smile vector mark. | Scales inside 48x48 badge circle | High | Available | tech-aws.svg | Rendered in TechStack cloud group.
Home (/) & Solutions | TechStack (Cloud) | Microsoft Azure Vector Logo | Icon | SVG | 48 | 48 | 1:1 | Azure angular cloud vector mark. | Scales inside 48x48 badge circle | High | Available | tech-azure.svg | Rendered in TechStack cloud group.
Home (/) & Solutions | TechStack (Cloud) | Google Cloud Platform (GCP) Vector Logo | Icon | SVG | 48 | 48 | 1:1 | GCP multi-color geometric hexagon logo. | Scales inside 48x48 badge circle | High | Available | tech-gcp.svg | Rendered in TechStack cloud group.
Home (/) & Solutions | TechStack (DevOps) | Docker Whale Container Vector Logo | Icon | SVG | 48 | 48 | 1:1 | Docker blue whale container ship vector. | Scales inside 48x48 badge circle | High | Available | tech-docker.svg | Rendered in TechStack DevOps group.
Home (/) & Solutions | TechStack (DevOps) | Kubernetes Helm Wheel Vector Logo | Icon | SVG | 48 | 48 | 1:1 | Kubernetes 7-spoke ship helm vector. | Scales inside 48x48 badge circle | High | Available | tech-kubernetes.svg | Rendered in TechStack DevOps group.
Home (/) & Solutions | TechStack (Data) | PostgreSQL Elephant Vector Logo | Icon | SVG | 48 | 48 | 1:1 | PostgreSQL Slonik elephant vector logo. | Scales inside 48x48 badge circle | High | Available | tech-postgresql.svg | Rendered in TechStack data group.
Home (/) & Solutions | TechStack (Data) | Redis In-Memory Vector Logo | Icon | SVG | 48 | 48 | 1:1 | Redis stacked ruby database cubes logo. | Scales inside 48x48 badge circle | Medium | Available | tech-redis.svg | Rendered in TechStack data group.
Global (All Pages) | GlobalFloatActions & Header | Direct Phone Dial Icon | Icon | SVG | 24 | 24 | 1:1 | Instant phone call floating FAB button and contact card icon. | Mobile bottom dock & Desktop right floating action pill | High | Available | lucide-phone.svg | Rendered via lucide-react Phone component.
Global (All Pages) | GlobalFloatActions & Header | WhatsApp Instant Chat Icon | Icon | SVG | 24 | 24 | 1:1 | Direct WhatsApp API messaging trigger for prospective clients. | Mobile bottom dock & Desktop floating action button | High | Available | lucide-message-circle.svg | Rendered via lucide-react MessageCircle component.
Global (All Pages) | GlobalFloatActions | Scroll-To-Top Arrow Icon | Icon | SVG | 20 | 20 | 1:1 | Elevated quick-return scroll FAB button. | Desktop & Mobile bottom corner | Medium | Available | lucide-arrow-up.svg | Rendered via lucide-react ArrowUp component.
Global (All Pages) | Header Navigation | Theme Toggle (Sun / Moon) Icons | Icon | SVG | 20 | 20 | 1:1 | Switch between light and dark visual themes across the application. | Header right controls on Desktop and Mobile navigation drawer | High | Available | lucide-sun-moon.svg | Rendered via lucide-react Sun and Moon components.
Global (All Pages) | Header & Drawers | Mobile Hamburger & Close Icons | Icon | SVG | 24 | 24 | 1:1 | Mobile navigation menu trigger and modal dismiss icon. | Mobile viewport only (<1024px) | High | Available | lucide-menu-x.svg | Rendered via lucide-react Menu and X components.
About (/about) | GlobalDeliverySection | Map Geolocation Pulsing Pin Marker | Icon | SVG | 32 | 32 | 1:1 | Pulsing geo-beacon pin placed at exact GPS coordinates for Chennai, US, UK, Canada, UAE. | Scales precisely relative to world map container coordinates | High | Available | map-pin-pulse.svg | Custom animated SVG element with CSS ripple ring animation.

## Logos & Brand Assets
Page | Section | Image / Icon Title | Asset Type | File Format | Required Width (px) | Required Height (px) | Aspect Ratio | Description / Purpose | Desktop / Tablet / Mobile Requirement | Priority | Current Asset Status | Recommended File Name | Notes
Global (All Pages) | Header & Navigation | Primary SVaaN Brand Logo (Light Theme) | Logo | SVG | 160 | 40 | 4:1 | Primary corporate vector logo with SVaaN typography and tech mark for light backgrounds. | Desktop: 160x40; Mobile: 130x32 with crisp vector scaling | High | Available | Primary_logo.svg | Active in /public (41.4 KB). Primary brand anchor across all page headers.
Global (All Pages) | FooterV2 & Dark Themes | Primary SVaaN Brand Logo (Inverted / White) | Logo | SVG | 160 | 40 | 4:1 | Pure white / transparent reverse version of the SVaaN corporate logo for dark footer backgrounds. | Desktop: 160x40; Mobile: 140x35 | High | Needs Replacement | svaan-logo-white.svg | Currently wrapped in an extra white badge container in FooterV2. Adding a native white SVG will enable a cleaner, modern transparent footer.
Global (Browser Tab) | Browser Head | SVaaN Brand Favicon Vector | Logo | SVG | 48 | 48 | 1:1 | Clean vector brand favicon rendered in modern desktop and mobile browsers. | Browser tab bar & bookmark icon | High | Available | favicon.svg / icon.svg | Active in /public and /src/app/icon.svg. Crisp multi-DPI rendering.
Mobile OS Home Screen | Apple Web Clip & PWA | Apple Touch Icon (iOS Home Screen) | Logo | PNG | 180 | 180 | 1:1 | High-resolution square icon with brand blue background for iOS "Add to Home Screen". | Mobile iOS Safari homescreen bookmark | Medium | Missing | apple-touch-icon.png | Recommended for mobile web app standards and high-resolution bookmarks.
Mobile Android / PWA | Web App Manifest | Android Chrome Web App Icons (192x192 & 512x512) | Logo | PNG | 512 | 512 | 1:1 | PWA compliant icons with standard and maskable padding for Android mobile launchers. | Android Chrome PWA prompt & splash screen | Medium | Missing | icon-192.png / icon-512.png | Required for complete PWA compliance and Lighthouse 100/100 PWA audit.
Social Media / Sharing | OpenGraph & Twitter Card | Default OpenGraph Social Share Card | Image | PNG / WebP | 1200 | 630 | 1.91:1 | Rich preview image displayed when sharing SVaaN website links on LinkedIn, Twitter/X, Slack, and WhatsApp. | Global social media sharing standard: 1200x630 pixels | High | Needs Replacement | og-svaan-enterprise.png | Currently falls back to square herosection.webp. A dedicated 1200x630 banner with logo, value proposition, and brand gradient is required.
Home (/) & Work | ClientExperiences / Proof | Client Partner Vector Logos (5 Brands) | Logo | SVG | 180 | 60 | 3:1 | Clean monochrome SVG vector marks for Biblical Touring, Fareeda Homecare, Siloam, MMU, and Havendeeds. | Desktop: Marquee client strip; Mobile: 2-col logo grid | High | Needs Replacement | client-logos-[client].svg | Currently rendered as styled typography tags in client stories. Vector client logos will elevate enterprise authority.
Security (/security-trust) | Compliance & Standards | SOC 2, ISO 27001, HIPAA & GDPR Trust Badges | Logo | SVG / PNG | 120 | 120 | 1:1 | Security certification and data compliance insignias for enterprise credibility. | Security & Trust page badge grid | Medium | Missing | badge-soc2.svg / badge-hipaa.svg | Reinforces enterprise trust with US and healthcare clients (Siloam, Fareeda Homecare).

## Animations & Micro-Interactions
Page | Section | Image / Icon Title | Asset Type | File Format | Required Width (px) | Required Height (px) | Aspect Ratio | Description / Purpose | Desktop / Tablet / Mobile Requirement | Priority | Current Asset Status | Recommended File Name | Notes
Global (All Pages) | Background Layer | Mouse-Tracking Interactive Radial Ambient Orbs | Animation | CSS / Canvas / Framer Motion | 600 | 600 | 1:1 | Smooth glowing ambient orbs that follow viewport coordinates with heavy hardware-accelerated blur (200px). | Desktop: Active mouse tracking; Mobile: Fixed subtle background glow (low CPU mode) | High | Available | RadialOrbEffect (CSS var(--t-orb-opacity)) | Configured in layout.tsx and individual page sections. Zero-lag CSS transform execution.
Global (Desktop Only) | CustomCursor Component | Smooth Follower Ring & Hover Expansion Dot | Animation | React / Framer Motion | 32 | 32 | 1:1 | Custom smooth cursor follower that expands into a ring when hovering interactive cards and links. | Desktop only (pointer: fine); Automatically disabled on touchscreen / mobile | Medium | Available | CustomCursor.tsx | Implemented with pointer-events-none and requestAnimationFrame spring physics.
Home & Solutions | Marquee Component | Infinite Seamless Horizontal Logo / Tech Marquee | Animation | CSS Keyframe (@keyframes marquee) | 1920 | 80 | 24:1 | Smooth 40s linear infinite loop ticker with hover-to-pause functionality. | Full viewport width across desktop, tablet, and mobile with hardware acceleration | High | Available | Marquee.tsx / globals.css | Uses will-change: transform and translates -50% for seamless looping.
Home & Header | Availability Beacon | Pulsing Live Status Indicator ("Available for projects") | Animation | CSS Keyframe (@keyframes pulse) | 12 | 12 | 1:1 | Green glowing radar beacon indicating immediate engineering availability for enterprise clients. | Inline badge next to header CTA and hero section | Medium | Available | BeaconPulse (Tailwind animate-pulse) | Lightweight SVG / CSS ripple effect.
About (/about) | GlobalDeliverySection | Geo-Coordinates Radar Ripple on World Map | Animation | CSS Keyframe (@keyframes ping) | 40 | 40 | 1:1 | Concentric radar rings pulsing around Chennai HQ, New York, London, Toronto, and Dubai pins. | Scales with SVG map container without impacting frame rate | High | Available | MapHotspotPulse (CSS) | Built into AboutSection map overlay with tooltips.
Capabilities & Solutions | ServiceDetailClient | Interactive Accordion Expand & Stagger Reveal | Animation | Framer Motion Layout | 1200 | Auto | Flexible | Spring-damped physics animations when expanding capabilities, deliverables, and service journeys. | Universal responsive layout transition across all devices | Medium | Available | AnimatePresence / motion.div | Ensures tactile feel and enterprise polish.